## Sheet1
| WDD_Project_2025 Group G | Done Y/N? | Team Member
Week | Goals for this week
week 8
| read brief & be familiar with it | y | Dreke, Alexander, Tristan, Andrei
| brainstorm with group - what sustainability goal to use | y | Dreke, Alexander, Tristan, Andrei
| team member strengths and weaknesses | y | Derek: leadership, Tristan: Creative, Alex: Html & Design, Andrei: Technicality & Github
| 1 person creates a shared folder and shares it! | y | Andrei
| my own wireframe | y | Dreke, Alexander, Tristan, Andrei
| sitemap for whole website | y | Dreke, Alexander, Tristan, Andrei | Tristand and Alexander did most
week 9 | add your tasks and assign them to a team member |  | Alexander | landing pages
|  |  | Tristan | info pages
|  |  | Derek | contact us & info pages
|  |  | Andrei | Sources & Report pages
| record who contributed - meeting and coding | y | evryone present and contributing as of 09/11/2025
Let Emer know if someone is out of contact
week 10 | add your tasks and assign them to a team member
Let Emer know if someone is out of contact
week 11 | add your tasks and assign them to a team member
Let Emer know if someone is out of contact
week 12 | finish up code
deploy website
testing - functional testing, speed test
Write/record report
only one CSS file - if possible more marks
testing menu links work
comments in HTML, CSS and JS
Make sure the author name is on each webpage
everyone has DOM manipulation on their own webpage
Submission | SUNDAY
| decide who does this | Andrei | Derek | Tristan | Alex