## task progress
| WDD_Project_2025 Group G | Done Y/N? | Team Member | NOTES/Comments
Week | Goals for this week
week 8
| read brief & be familiar with it | y | Derek, Alexander, Tristan, Andrei
| brainstorm with group - what sustainability goal to use | y | Derek, Alexander, Tristan, Andrei
| team member strengths and weaknesses | y | Derek: leadership, Tristan: Creative, Alex: Html & Design, Andrei: Technicality & Github
| 1 person creates a shared folder and shares it! | y | Andrei
| my own wireframe | y | Derek, Alexander, Tristan, Andrei
| sitemap for whole website | y | Derek, Alexander, Tristan, Andrei | Tristan and Alexander did most
week 9 | add your tasks and assign them to a team member
| Pages assigned Contact/ Info | y | Alexander | landing pages
| Pages assigned conservation/ Find us pages | y | Tristan | info pages
| Pages assigned Irish water / Sources | y | Derek | contact us & info pages
| Pages assigned Langing Page/News | y | Andrei | Sources & Report pages
| record who contributed - meeting and coding | y | everyone present and contributing as of 09/11/2025 Teams Meetings held every week
| Let Emer know if someone is out of contact | y | everyone present and contributing as of 16/11/2025 Teams Meetings held every week
| Weekly meeting set up on teams for collaboration between group memebers | y | everyone present and contributing as of 23/11/2025 Teams Meetings held every week
week 10 | add your tasks and assign them to a team member
| Update report | y | All
| sitemap updated | y | Alexander, Tristan
| design board updated | y | tristan
| navbar improvement | y | Alexander
| procedural navbar (change one file change it on every page) | y | Andrei
| javascript buttons to hide | y | Derek
| Let Emer know if someone is out of contact |  | everyone present and contributing as of 22/11/2025
week 11 | add your tasks and assign them to a team member
| functionality= what does the page do? and does it do it well? |  | All
| form validation on each page |  | All
Let Emer know if someone is out of contact
week 12 | finish up code
deploy website
testing - functional testing, speed test
Write/record report
only one CSS file - if possible more marks
testing menu links work
comments in HTML, CSS and JS
Make sure the author name is on each webpage
everyone has DOM manipulation on their own webpage
Submission | SUNDAY
decide who does this
Andrei Derek Tristan Alexander
Team Member | Tasks | Completed | Notes/comments/blockers
Alexander | Footers to be added to pages | COMPLETED | completed by derek and andrei
Tristan | css page to be merged with main css pages | COMPLETED | Completed by derek
Derek | fix cover page picture on report | COMPLETED | pfd created
Andrei | checkpoint 2 uploaded Sunday night | In-Progress | Check point pdf created and uploaded
Alexander | js scrips completed and Css file merged with main css | In-Progress | Script for footer to be Changed to reflect a sticky/absloute postion at bottom of page
All | Discission needed on what to actully put in website if anything or do we do loruem ipsum | To Be Started | What research needs to be done
All | Discission needed on forms and DOM to be inpemented | To Be Started | Elemets that make sense for a website or just show functionality
Alexander | Update needed on progression with pages | In-Progress | ????????????????????????????????????????????????????????????????????????????????????????????

## lists
name | code type | object type | names for html files
All | css | buttons | index | WEEK 9 | COMPLETED
Alexander | html | list | news | WEEK 10 | In-Progress
Tristan | javascript | text | uisceire | WEEK 11 | To Be Started
Andrei |  | image | sources | WEEK 12 | More Time Needed
Derek |  | div | conserv | WEEK 13
Team/Unassigned |  | links | findus | WEEK 14
|  |  | contactus | WEEK 15
|  |  | info | WEEK 16